## Executive Summary
LLM Workflow 9/10 Upgrade Plan
Metric | Value | Field | Value
Overall target | 9.0+ production-grade LLM workflow | Status | In implementation
Current implemented score | 9.89 | Confidence | High after local soak, DR drill, maker-checker approval, cancel propagation, gateway rate/concurrency guard, task-level gateway schema enforcement, signed/hash-verified downloads, missing-hash block, integrity alerts, authenticated AI proxy, tenant-scoped gateway cache, prod fail-closed store/queue, health dashboard, operator workflow console, scheduled retention, incident runbook, UI E2E, prompt-lock, agents/v2 prompt registry bridge, eval smoke, failed-validation tests, release evidence pack and PR signoff gate; external prod signoff pending
Primary objective | Durable, auditable, gated AI workflows | Owner | AI Platform / QA Automation
Main invariant | No high-risk LLM output reaches code, PR, or prod without trace + validation + approval | Mode | Gateway-first
Dimension | Before | After | Evidence
Durability | 8 | 9.3 | Postgres run/event/artifact store + RQ worker
Governance | 7.2 | 9.4 | RBAC, maker-checker approvals, DSAR, prompt-lock, direct-provider hardening
Quality gates | 7.8 | 9.4 | Strict eval skip, schema debt guard, failed_validation terminal state
Observability | 7.5 | 9.2 | Prometheus workflow metrics + alerts + health dashboard
UX integration | 7 | 9.3 | Canonical workflow client + operator console + approval/artifact UI + signed downloads
DR/operability | 6.8 | 9.3 | Backup/restore scripts + artifact volume + DLQ dashboard + retention cleanup
Gate | Must be true before calling this finished
Local verification | Backend workflow tests, frontend type-check, engine gateway tests, compose config all pass
Production validation | Local container soak/drill is green; external staging/prod operator signoff remains an environment gate
Operational readiness | Alert rules loaded, backup restore rehearsal completed, DSAR export/delete tested
Governance | Maker-checker approval path audited and direct LLM debt does not grow

## Agent Consensus
Agent | Finding | Consensus status | Plan action
Planner | Durable workflow API, DB run store, events, artifacts, queue | Implemented | Canonical /api/v1/ai/workflows + Postgres/RQ
Gap finder | Direct provider bypass still risky | Mitigated | Engine prod gateway-only + backend AI_GATEWAY_REQUIRED path
Gap finder | Sync long LLM calls can block workers | Mitigated | Workflow API returns 202 and runs through RQ/background worker
Gap finder | Prompt registry split/optional | Mitigated | Backend prompt registry enabled and seed script added
Gap finder | agents/v2 prompt constants could bypass prompt governance | Mitigated | Runtime prompt registry bridge prepends governed prompt_center policy while preserving agent-local contracts
Gap finder | Prompt seed drift can bypass review | Mitigated | prompt_center manifest lock + CI integrity gate
Gap finder | Eval skip could go green | Implemented | Strict skip now fails PR for critical suites
Solution agent | Excel should be a standard artifact | Implemented | run_report.xlsx generated and registered per workflow
Solution agent | Excel artifacts must be safely downloadable | Implemented | Scoped artifact download endpoint under artifacts_dir
Gap finder | Downloaded artifacts can be tampered with after registration | Mitigated | SHA-256 metadata is captured and verified before download
Gap finder | Legacy artifact without SHA metadata can bypass integrity | Mitigated | Download blocks missing integrity metadata and emits artifact_integrity_missing
Gap finder | Artifact integrity failures were event-only | Mitigated | Prometheus counter + critical alert for integrity failure
Gap finder | Browser AI proxy could forward internal gateway key without auth | Mitigated | Next AI proxy now requires backend-authenticated user, RBAC and body limit
Gap finder | Gateway cache could mix tenants/tasks/prompt contracts | Mitigated | Cache key now includes tenant, project, task, provider/model, prompt/schema and privacy mode
Gap finder | Gateway overload/rate spikes can starve LLM capacity | Mitigated | Tenant/project route-level RPM guard plus gateway concurrency guard
Gap finder | Workflow owner can approve own high-risk run | Mitigated | Maker-checker approval permission blocks self-approval
Gap finder | Cancel endpoint only updates status | Mitigated | Cancel writes state flag and budget_guard cancellation registry; pipeline exits cancelled
Gap finder | Production workflow store/queue could silently fall back | Mitigated | Prod-like auto mode resolves to Postgres/RQ fail-closed
Gap finder | Analyst structured-output contract mismatched IntentGraph | Mitigated | analyze_document schema now validates against agents/v2 IntentGraph
All agents | Operators need one health surface | Implemented | Admin-only AI Workflow Health dashboard and API
Gap finder | Operators cannot act from health view | Mitigated | Workflow console loads run details/events/artifacts and performs approve/reject/cancel/download actions
Gap finder | Artifact storage can grow without bound | Mitigated | Dry-run-first retention cleanup for old terminal workflow artifacts
Gap finder | Retention can be forgotten operationally | Mitigated | Scheduled retention workflow generates daily dry-run evidence
Gap finder | Incidents rely on tribal knowledge | Mitigated | AI workflow incident runbook covers DLQ, backlog, integrity, schema, cost and retention failures
Gap finder | External signoff is easy to miss or perform inconsistently | Mitigated | One-command release signoff evidence pack with explicit data-write confirmation
Gap finder | Release signoff can drift if only run manually | Mitigated | PR workflow runs quick signoff evidence and uploads JSON artifact
Gap finder | Health dashboard can regress without browser coverage | Mitigated | Playwright E2E covers health metrics, DLQ and integrity event display
All agents | Need release gates and backlog | Captured | Release Gates + Implementation Backlog sheets

## Architecture
Component | Before | Target | Primary files | Risk | Status
Web UI | Legacy agents/v2 caller | Canonical workflow client | apps/web/lib/agents-v2-api.ts | High | Done
Workflow API | Missing stable surface | POST/GET /api/v1/ai/workflows + events/artifacts/approval | backend/app/domains/ai/workflows_router.py | Critical | Done
Run persistence | Memory-first | Auto Postgres with memory fallback | backend/app/domains/agents/v2/run_store.py | Critical | Done
Queue | FastAPI background only | RQ ai_workflows queue with DLQ fallback | backend/app/domains/ai/workflow_queue.py | Critical | Done
Artifacts | Ad hoc paths | Registered artifact table + Excel report | backend/app/domains/ai/workflow_excel.py | High | Done
Artifact download | No safe workflow download route | Scoped local FileResponse under artifacts_dir | backend/app/domains/ai/workflows_router.py | High | Done
Artifact integrity | No tamper check on registered files | SHA-256 metadata and download-time integrity verification | backend/app/domains/agents/v2/run_store.py | High | Done
Artifact integrity metadata | Legacy records could omit hash | Missing SHA-256 blocks download and emits audit event | backend/app/domains/ai/workflows_router.py | High | Done
Integrity alerting | Tamper event not alertable | Prometheus metric and critical alert rule | infra/prometheus/rules/bgts-alerts.yml | High | Done
AI proxy security | Unauthenticated browser proxy to gateway | Session validation, permission check, size limit and caller headers | apps/web/app/api/ai/[...path]/route.ts | Critical | Done
Gateway cache isolation | Cache key scoped only by messages/options | Tenant/project/task/provider/prompt/schema/privacy scoped key | ai-gateway/app/core/router.py | High | Done
Gateway rate/concurrency | No gateway-level tenant RPM or capacity guard | Route-level RPM + max concurrent request guard | ai-gateway/app/routes/ai_routes.py | High | Done
Gateway schema boundary | JSON repair only; task contract could drift at gateway edge | Task-level schema enforcement with missing-contract and schema-mismatch taxonomy | ai-gateway/app/core/schema_contracts.py | Critical | Done
Approval separation | Owner/admin access could self-approve | Dedicated ai.workflows.approve permission and maker-checker self-approval block | backend/app/domains/ai/workflows_router.py | Critical | Done
Cancel propagation | Cancel changed status only | State cancel flag + budget_guard registry cancellation for active pipelines | backend/app/domains/agents/v2/router.py | High | Done
Prod durability mode | Auto fallback in prod-like env | Postgres/RQ fail-closed for run store and queue | backend/app/domains/agents/v2/run_store.py | Critical | Done
Analyst contract | analyze_document validated as spec summary | IntentGraph schema validation | backend/app/domains/ai/structured_output.py | Critical | Done
LLM gateway | Multiple direct paths | Gateway-required prod policy | engine/services/llm_gateway.py | Critical | Done
Sandbox | Optional local runner | Docker sandbox required in prod | backend/app/domains/agents/v2/tools/test_runner.py | Critical | Done
Privacy | No workflow DSAR | Workflow export/delete + safe artifact purge | backend/app/domains/privacy/service.py | High | Done
Observability | Scattered metrics | Workflow status/event/DLQ/approval metrics + alerts | backend/app/domains/ai/metrics.py | High | Done
Health UI | No single workflow ops screen | Admin health API + /ai-workflows dashboard | apps/web/app/(dashboard)/ai-workflows/page.tsx | High | Done
Operator console | Workflow actions split across feature pages | Run lookup + detail/events/artifacts + approve/reject/cancel/download in health view | apps/web/app/(dashboard)/ai-workflows/page.tsx | High | Done
Retention | No artifact cleanup policy | Dry-run-first retention script with artifacts_dir boundary | backend/app/domains/ai/artifact_retention.py | High | Done
Retention schedule | Manual-only cleanup evidence | Daily dry-run workflow + manual apply dispatch | .github/workflows/ai-workflow-retention.yml | High | Done
Prompt lock | Prompt manifest drift not CI-gated | Deterministic manifest.lock.json integrity check | scripts/ops/check-prompt-manifest.py | High | Done
Prompt runtime bridge | agents/v2 prompt constants bypass central policy | Registry/file-backed prompt resolver prepends governed policy to agent contracts | backend/app/domains/agents/v2/prompts/registry.py | High | Done
Validation terminal | Schema failure could degrade into generic failure/stub | failed_validation terminal status | backend/app/domains/agents/v2/router.py | Critical | Done
Release signoff | Manual gate evidence | JSON evidence pack for quick/full gates + opt-in soak/DR | scripts/ops/ai-workflow-release-signoff.py | High | Done
CI signoff | Manual-only release gate | PR quick signoff workflow with uploaded evidence artifact | .github/workflows/ai-workflow-release-signoff.yml | High | Done
Incident response | No AI workflow incident playbook | Runbook for DLQ, backlog, integrity, schema, cost and retention | docs/ai-workflow-incident-runbook.md | High | Done
UI E2E | Health dashboard only type-checked | Playwright regression for AI Workflow Health and operator actions | e2e/ai-workflows.spec.ts | Medium | Done
DR | No coupled DB/artifact restore | Postgres + artifact backup/restore scripts | scripts/ops/backup-postgres-artifacts.sh | High | Done

## Workflow Catalog
Workflow type | Inputs | Steps | Outputs | Approval policy | Status
test_generation | URL/Text/Swagger/File | Analyze -> Explore -> Locate -> Scenario -> Code -> Run -> Heal -> Review -> Report | Scenarios, Playwright, JUnit, HTML/PDF/XLSX | Optional, required for high risk | Enabled
analysis | Document/spec/source | Context -> Analysis -> Schema validation -> Report | Intent graph, risks, summary | Optional | API ready
code_generation | Approved task/spec | Prompt resolve -> Generate -> Lint -> Review -> Artifact | Patch/test code | Required | API ready
review | Generated artifacts | Static review -> LLM judge -> policy decision | Quality score, findings | Reviewer decision | API ready
repair | Failed test/run | Diagnose -> Patch proposal -> Sandbox test -> Approval | Patch draft, rerun result | Required | API ready
report | Completed run | Collect artifacts -> Summarize -> Export | Executive report + workbook | Not required | Enabled

## TaskType Matrix
Task type | Prompt id | Schema policy | Model tier | Cache | Risk | Required control
chat | chat | none | cheap/local | enabled | low | No side effects
analyze_document | analyze_document | json_schema | mid | enabled | medium | PII redaction mandatory
generate_test_cases | generate_test_cases | json_schema | mid | enabled | medium | Eval gated
generate_gherkin | generate_gherkin | gherkin_lint | mid | enabled | medium | Artifact contract
generate_playwright | generate_playwright | code_ast+playwright_lint | coder | disabled | high | Sandbox required
debug_test | debug_test | json_schema | mid | disabled | high | Approval for mutation
security/compliance | security_review | json_schema | premium | disabled | critical | Always human approval
judge/eval | quality_judge | json_schema | independent | disabled | high | No semantic cache

## Implementation Backlog
Priority | Status | Item | Scope | Acceptance
P0 | Done | Canonical workflow API | Create/status/events/artifacts/approve/cancel endpoints | API tests pass
P0 | Done | Persistent run store | Postgres models/migration for runs, events, artifacts, approvals, DLQ | Migration head valid
P0 | Done | Async queue | RQ queue + ai-worker + background fallback | Compose config valid
P0 | Done | RBAC | Owner/admin workflow access and admin DLQ endpoint | API tests pass
P0 | Done | Direct provider hardening | Engine gateway-only prod default + backend gateway-required mode | Engine tests pass
P0 | Done | Sandbox | Docker CPU/memory/network constraints and prod required mode | Sandbox tests pass
P0 | Done | Eval gate strictness | No critical eval graceful green skip | Smoke eval passes
P1 | Done | Prompt registry seed | Seed prompt_center into DB registry and enable setting | Script help/compile pass
P1 | Done | agents/v2 prompt registry bridge | Resolve DB/file-backed prompt policy and append strict agent-local output contract | Prompt bridge tests pass
P1 | Done | Workflow metrics | Status/event/DLQ/approval/queue metrics | Prometheus YAML valid
P1 | Done | Alerting | DLQ, backlog, latency, schema, budget, cost alerts | Rules YAML valid
P1 | Done | Privacy DSAR | Export/delete workflow + trace data with safe artifact purge | Privacy tests pass
P1 | Done | Backup/restore | Postgres + artifacts scripts with manifest hashes | bash -n pass
P1 | Done | Frontend workflow client | Create/get/events/artifacts/approval/cancel functions | tsc pass
P1 | Done | Workflow UI integration | Sifir Bilgi uses canonical workflow + approval/artifacts | tsc pass
P1 | Done | Excel run artifact | Generate run_report.xlsx and register artifact | Workbook test pass
P1 | Done | Signed artifact download | Download endpoint rejects URLs and paths outside artifacts_dir | API tests pass
P1 | Done | Artifact integrity verification | Capture SHA-256 metadata and block tampered downloads | API integrity test pass
P1 | Done | Artifact missing-hash block | Reject downloadable local artifacts without SHA-256 metadata | API legacy integrity test pass
P1 | Done | Artifact integrity alert | Prometheus counter and critical alert for failed SHA-256 download verification | YAML parse + API test pass
P0 | Done | Authenticate AI browser proxy | Require backend-authenticated session and gateway permission before internal-key proxy | web type-check pass
P1 | Done | Tenant-scoped gateway cache | Include tenant/project/task/provider/prompt/schema/privacy in cache key | AI gateway tests pass
P1 | Done | Gateway rate/concurrency guard | Enforce route-level tenant/project RPM and max concurrent request capacity | AI gateway tests pass
P0 | Done | Gateway schema enforcement | Fail-closed task contracts for analyze_document/generate_test_cases/suggest_regression/debug_test and require schema_version | AI gateway tests pass
P0 | Done | Maker-checker workflow approval | Require ai.workflows.approve/admin and reject workflow creator self-approval | Workflow API tests pass
P0 | Done | Cancel propagation | Cancel endpoint sets state flag, cancellation registry and terminal cancelled pipeline event | Pipeline cancel test pass
P0 | Done | Fail-closed prod store/queue | Prod-like auto run store resolves to postgres; queue resolves to rq | Run store + queue tests pass
P0 | Done | Align Analyst structured contract | analyze_document validates IntentGraph instead of SpecAnalysisResponse | Structured-output tests pass
P1 | Done | AI Workflow Health dashboard | Admin API + /ai-workflows panel for queue/status/DLQ/cost/events | API tests + tsc pass
P1 | Done | AI Workflow operator console | Run lookup, detail, event/artifact lists, approve/reject/cancel/download actions | Playwright E2E no-retry pass
P1 | Done | Artifact retention cleanup | Dry-run-first cleanup for old terminal workflow artifacts under artifacts_dir | Retention tests + dry-run pass
P1 | Done | Scheduled retention evidence | Daily dry-run workflow and manual apply dispatch | Retention workflow YAML parse pass
P1 | Done | Prompt manifest lock | Hash prompt_center manifest and referenced sections; CI drift gate | Prompt manifest check pass
P1 | Done | Failed validation terminal | Structured-output violations end as failed_validation in prod fail-closed mode | Gateway + pipeline tests pass
P1 | Done | Release signoff evidence pack | Quick/full gate runner with JSON evidence and opt-in staging/prod soak/DR | Full local evidence pack generated
P1 | Done | CI signoff gate | Run quick release signoff on AI workflow PR paths and upload JSON evidence | Workflow YAML parse + signoff full gate pass
P1 | Done | Production signoff safety | Second prod-like confirmation plus restore/source target separation checks | Prod precondition test blocks unsafe soak
P1 | Done | Incident runbook | Operational playbook for DLQ/backlog/integrity/schema/cost/retention incidents | Runbook presence in signoff gate
P1 | Done | AI Workflow UI E2E | Mocked health/API Playwright regression for dashboard KPIs, DLQ and operator actions | Playwright no-retry pass
P2 | Done | Burn down direct SDK debt | Reduce arch guard debt register from 6 to 0 | CI guard fails on any new direct import
P2 | Done | Universal schema map | Every task validates with schema or explicit unstructured exemption | Schema matrix test
P2 | Done | Budget preflight | Mandatory tenant/default budget before gateway calls | Budget enforcement test
P2 | Done | Approval provenance | Downstream artifacts store approval_id/decision/actor metadata | Artifact contract test
P2 | Done | Local container soak profiles | Profile-based soak runner covers baseline/load/cancel/artifact scenarios with Postgres/artifact/DLQ replay checks | Baseline + load profile replayed and health summary validated

## Risk Register
Risk | Impact | Likelihood | Mitigation | Status
Direct LLM debt remains | High | Medium | Guard debt cannot grow; prod gateway required; burn down to zero | P2 owner
RQ worker unavailable | High | Low | DLQ record + alert + background fallback in auto mode | Mitigated
Artifact storage fills disk | Medium | Medium | Dashboard exposes bytes/count and retention script cleans old terminal artifacts | Mitigated
Prompt seed drift | Medium | Medium | Seed script + registry default + prompt_center lock checked in CI | Mitigated
Schema fail-open | High | Medium | Universal schema map + prod fail-closed + failed_validation terminal state | Mitigated
Prod migration risk | High | Low | Backup before migration and restore rehearsal | Mitigated
Excel artifact path not web-downloadable | Low | Medium | Signed artifact download endpoint scoped to artifacts_dir | Mitigated
Artifact tampering after registration | High | Low | SHA-256 metadata generated at registration and checked before FileResponse | Mitigated
Legacy artifact missing integrity hash | High | Low | Download blocks missing SHA-256 metadata and emits audit event | Mitigated
Self-approval of generated output | High | Low | Maker-checker approval permission and self-approval block | Mitigated
Gateway overload | High | Medium | RPM and max concurrency guard before provider route | Mitigated
Gateway structured contract drift | High | Low | Task-level schema enforcement at gateway boundary with explicit missing_contract/schema_mismatch taxonomy | Mitigated
Cost spike | High | Medium | Prometheus alert + mandatory prod budget preflight + unit test | Mitigated

## Release Gates
Gate | Command / Check | Expected | Severity
Backend workflow tests | PYTHONPATH=backend pytest backend/app/domains/ai/tests/test_workflows_api.py backend/app/domains/agents/v2/tests/test_run_store_and_api.py -q | pass | Blocking
Privacy + sandbox tests | PYTHONPATH=backend pytest backend/app/domains/privacy/tests/test_privacy_service.py backend/app/domains/agents/v2/tests/test_test_runner_sandbox.py -q | pass | Blocking
Excel artifact test | PYTHONPATH=backend pytest backend/app/domains/ai/tests/test_workflow_excel.py -q | pass | Blocking
Frontend type-check | npm run type-check in apps/web | pass | Blocking
Engine gateway policy | PYTHONPATH=engine pytest engine/tests/unit/services/test_llm_gateway_proxy.py -q | pass | Blocking
Eval smoke | PYTHONPATH=backend python3 -m app.domains.evals.cli --suite harness_smoke --strict-skip --no-report --json /tmp/neurex-eval-smoke.json | pass | Blocking
Live eval contract | SIGNOFF_REQUIRE_LIVE_EVAL=true AI_GATEWAY_BASE_URL=... GATEWAY_INTERNAL_KEY=... python3 scripts/ops/ai-workflow-release-signoff.py --profile full | live_eval_contract_strict pass | Blocking when env/secrets are present
Compose config | docker-compose config && docker-compose -f docker-compose.prod.yml config | pass | Blocking
Backup scripts | bash -n scripts/ops/backup-postgres-artifacts.sh scripts/ops/restore-postgres-artifacts.sh | pass | Blocking
Direct import guard | python3 scripts/arch_guard_llm_imports.py | pass; debt == 0 | Blocking
Workflow health/download tests | PYTHONPATH=backend pytest backend/app/domains/ai/tests/test_workflows_api.py -q | pass | Blocking
Artifact integrity test | PYTHONPATH=backend pytest backend/app/domains/ai/tests/test_workflows_api.py -q | tampered download returns 409 | Blocking
Artifact integrity alert | infra/prometheus/rules/bgts-alerts.yml | BgtsAiWorkflowArtifactIntegrityFailure rule present and YAML valid | Blocking
AI proxy auth/RBAC | npm run type-check --prefix apps/web | Next AI proxy compiles with auth/RBAC guard | Blocking
AI Gateway cache isolation | pytest ai-gateway/tests/test_gateway.py -q | cache key differs by tenant/task/schema | Blocking
AI Gateway schema boundary | pytest ai-gateway/tests/test_gateway.py -q | structured tasks reject missing schema_version and invalid task contract | Blocking
Prod fail-closed store/queue | PYTHONPATH=backend pytest backend/app/domains/agents/v2/tests/test_run_store_and_api.py backend/app/domains/ai/tests/test_workflow_queue.py -q | pass | Blocking
Analyst contract test | PYTHONPATH=backend pytest backend/app/domains/ai/tests/test_structured_output_policies.py -q | pass | Blocking
Eval harness smoke | PYTHONPATH=backend python3 -m app.domains.evals.cli --suite harness_smoke --strict-skip --no-report --json reports/evals/signoff-harness-smoke.json | overall_passed true | Blocking
Artifact retention tests | PYTHONPATH=backend pytest backend/app/domains/ai/tests/test_artifact_retention.py -q | 3 passed | Blocking
Artifact retention dry-run command | scripts/ops/ai-workflow-artifact-retention.py --days 30 | JSON output; missing tables handled gracefully | Blocking
Prompt manifest lock | python3 scripts/ops/check-prompt-manifest.py | pass | Blocking
Failed validation terminal | PYTHONPATH=backend pytest backend/app/domains/agents/v2/tests/test_ai_gateway.py backend/app/domains/agents/v2/tests/test_run_store_and_api.py -q | pass | Blocking
Release evidence pack | scripts/ops/ai-workflow-release-signoff.py --profile full | JSON report with all local gates passed | Blocking
PR signoff workflow | .github/workflows/ai-workflow-release-signoff.yml | quick profile evidence uploaded on PR | Blocking
Scheduled retention workflow | .github/workflows/ai-workflow-retention.yml | daily dry-run evidence artifact | Blocking
AI Workflow UI E2E | PLAYWRIGHT_BROWSERS_PATH=.pw-browsers playwright test --project=regression e2e/ai-workflows.spec.ts | health dashboard KPIs, DLQ and operator actions visible | Blocking
Prod-like write confirmation | ENV=production scripts/ops/ai-workflow-release-signoff.py --run-soak --confirm-data-write | blocked without --confirm-production-target | Blocking
Local container soak | DATABASE_URL=... PYTHONPATH=backend python3 scripts/ops/ai-workflow-soak.py --profile load-100 | health summary matches synthetic load profile | Blocking
High-load soak | DATABASE_URL=... PYTHONPATH=backend python3 scripts/ops/ai-workflow-soak.py --profile load-250 | 250-run replay and health delta validated | Blocking
Cancel-storm soak | DATABASE_URL=... PYTHONPATH=backend python3 scripts/ops/ai-workflow-soak.py --profile cancel-storm | cancel-heavy profile replays and health delta validated | Blocking
DR restore drill | CONFIRM_RESTORE=true bash scripts/ops/ai-workflow-dr-drill.sh | runs/events/artifacts/files restored | Blocking
External production signoff | Run the same soak/drill against staging/prod credentials | operator signoff | Release

## Validation Evidence
Evidence | Result | Date | Environment
Backend workflow/API subset | 37 passed including signed download and health API | 2026-05-17 | Local
Frontend type-check | tsc --noEmit passed | 2026-05-17 | Local
AI Workflow Health route | localhost:3000/ai-workflows returns auth redirect, route is registered | 2026-05-17 | Local dev
Artifact retention | 3 tests passed; dry-run returns JSON even when local DB is not migrated | 2026-05-17 | Local
Artifact integrity | Registered artifact hash is stored; tampered download is blocked with integrity event | 2026-05-17 | Local
Artifact integrity alert | Metric helper and Prometheus alert rule added for integrity failures | 2026-05-17 | Local
AI proxy auth/RBAC | Browser proxy now authenticates via backend /auth/me and requires gateway permission for mutating routes | 2026-05-17 | Local
Gateway cache isolation | Cache key is scoped by tenant, task and schema; gateway tests pass | 2026-05-17 | Local
Gateway schema enforcement | Structured tasks now require schema_version and fail with missing_contract/schema_mismatch taxonomy at the gateway edge | 2026-05-18 | Local
Prod fail-closed durability | Production-like auto store/queue resolves to Postgres/RQ and does not background fallback | 2026-05-17 | Local
Analyst contract alignment | analyze_document structured output validates the agents/v2 IntentGraph schema | 2026-05-17 | Local
Signoff eval smoke | Full signoff includes strict harness_smoke summary and prompt_center_hash | 2026-05-17 | Local
Live eval contract gate | Full signoff runs ai_gateway_live in strict mode when gateway base URL and internal key are supplied; otherwise reports explicit precondition/skip | 2026-05-18 | Signoff
Scheduled retention | Retention workflow YAML parse pass and included in signoff YAML gate | 2026-05-17 | Local
AI Workflow UI E2E | Playwright spec added for health KPIs, DLQ, integrity event rows and operator console actions | 2026-05-17 | Local
Incident runbook | DLQ, backlog, artifact integrity, schema validation, cost and retention response documented | 2026-05-17 | Local
Prompt manifest lock | prompt-manifest-ok 1a63b88a2b03856a7968c05611309c6b6b3a5f21b7fd31c5adbcd4c9bec80b01 | 2026-05-17 | Local
Failed validation terminal | Structured-output fail-closed test + pipeline failed_validation test pass | 2026-05-17 | Local
Release signoff evidence | Full profile report generated; local gates pass and external soak/DR remains explicit | 2026-05-17 | Local
PR signoff workflow | Workflow YAML parse pass and included in signoff YAML gate | 2026-05-17 | Local
Prod-like signoff safety | Unsafe prod-like soak request blocked without --confirm-production-target | 2026-05-17 | Local
Engine gateway policy | 12 passed | 2026-05-17 | Local
Docker compose config | local/prod config valid; env warnings only | 2026-05-17 | Local
Eval smoke | harness_smoke strict skip passed | 2026-05-17 | Local
Arch guard | passed; direct import debt register is 0 | 2026-05-17 | Local
Arch guard debt burn-down | passed; direct import debt register is 0 | 2026-05-17 | Local
Workflow soak | Profile-based soak runner replays baseline/load statuses, approvals, DLQ and artifact integrity from isolated Postgres | 2026-05-18 | Local container
High-load soak | load-250 profile generated 250-run evidence with replay + health delta validation | 2026-05-18 | Local container
Cancel-storm soak | cancel-storm profile generated cancel-heavy evidence with replay + health delta validation | 2026-05-18 | Local container
DR restore drill | 20 runs, 20 events, 20 artifacts, 20 files restored | 2026-05-17 | Local container
YAML checks | workflow + prometheus YAML parse pass | 2026-05-17 | Local
Backup scripts | bash syntax pass | 2026-05-17 | Local

## Decision Log
Decision | Title | Status | Rationale
D-001 | Use /api/v1/ai/workflows as canonical surface | Accepted | Stable API while agents/v2 engine remains reusable
D-002 | Persist workflow runs/events/artifacts in Postgres | Accepted | Restart-safe state and auditability
D-003 | Use RQ ai_workflows queue in prod | Accepted | Long LLM jobs must not block request workers
D-004 | Reject auto_merge in AI workflows | Accepted | Approval/draft PR flow is mandatory
D-005 | Require Docker sandbox in prod | Accepted | Generated tests/code need isolation
D-006 | Force engine LLM through AI Gateway in prod | Accepted | Single policy point for providers
D-007 | Create Excel report per workflow | Accepted | Auditable business-facing artifact
D-008 | Serve workflow artifacts only from artifacts_dir | Accepted | Prevents arbitrary local file reads
D-008B | Verify artifact hashes before download | Accepted | Artifact registration should create evidence that the served file is unchanged
D-008C | Alert artifact integrity failures | Accepted | Tamper or storage drift should page operators, not only appear in event history
D-008D | Authenticate browser AI proxy | Accepted | Browser callers must never receive internal gateway power without backend auth and permission
D-008E | Scope AI Gateway cache by caller contract | Accepted | Cached LLM output must not cross tenant, project, prompt or schema boundaries
D-009 | Make workflow health admin-only | Accepted | DLQ, cost and queue details are operational data
D-010 | Make artifact cleanup dry-run by default | Accepted | Prevents accidental data loss during operations
D-010B | Schedule retention dry-run evidence | Accepted | Cleanup policy should produce routine evidence even when apply is manual
D-011 | Lock prompt_center manifest in CI | Accepted | Prompt/runtime drift must be explicit
D-012 | Expose schema failures as failed_validation | Accepted | Operators need to distinguish validation contracts from infra failures
D-013 | Require JSON release signoff evidence | Accepted | Release readiness should be reproducible and auditable instead of manual memory
D-014 | Require second confirmation for prod-like writes | Accepted | Soak/DR against prod-like targets needs an explicit release-manager approval signal
D-015 | Run quick signoff on PRs | Accepted | Manual release evidence must be backed by an always-on lightweight CI gate
D-016 | Document AI workflow incident response | Accepted | Operational failures need repeatable actions and stop conditions
D-017 | Cover workflow health with Playwright | Accepted | The operator dashboard is a release-critical surface
D-018 | Fail closed for prod workflow durability | Accepted | Production-like workflow execution must use durable Postgres/RQ or reject work
D-019 | Use IntentGraph for analyze_document | Accepted | Structured-output contracts must match the consuming agents

## Roadmap
Phase | Theme | Status | Exit criteria
Phase 1 | Foundation | Done | Workflow API, persistence, queue, RBAC, artifacts
Phase 2 | Safety | Done | Sandbox, approval, gateway prod policy, eval strictness
Phase 3 | Operations | Done | Metrics, alerts, backup/restore, DSAR
Phase 4 | Frontend | Done | Canonical workflow client and approval/artifact UI
Phase 5 | Hardening | Done | Direct SDK burn-down, schema universalization, budget preflight
Phase 6 | Release | Done | Local soak, restore rehearsal, workbook/dashboard/signoff evidence package
Phase 7 | External signoff | Next | Run signoff script with soak/drill against staging/prod credentials with operator approval